## Slide 1: Technology Connected Communities
The power of community elevates cultural learning
Technology: internet access; hardware/software; last mile connectivity
Connected: education outcomes; career readiness; public consciousness
Communities: shared truths; knowledge emissaries; cultural & linguistic integrity
Marthann Schulte, PhD – Project Director (marthannschulte@nmhu.edu)
A National Telecommunications and Information Administration funded project with the School of Education at New Mexico Highlands University

## Slide 2: Purpose of the Meeting
Share info about the TCC Project@NMHU
Question:
Are PED approvals needed for our credit recovery options?

## Slide 3
Federal grant – National Telecommunications and Information Administration (NTIA) - US Dept of Commerce
  Grant focuses on internet access & technology solutions in rural, underserved areas (infrastructure or education)
NMHU proposal emphasized education outcomes/options
  Dual credit & credit recovery - online learning modules
  ALGE content – cultural & linguistic
  Computers, internet boost, place based mentors
  Initial anchor community focus, then NNM expansion, then statewide
NMHU award announced October 2022 - Grant ends October 2024
Grant Origins & Status

## Slide 4: Full Service Community Schools
Las Vegas City Schools – anchor school
West Las Vegas Schools – anchor school
Cuba Independent School District
Pecos Independent School District
Peñasco Independent School District
Mora Public Schools
Isleta Elementary School
Lessons learned: Post-Covid learning needs; Busy calendars; Pooling resources; Improving outreach via the NTIA Grant
Expanded partnership with Professional Development Schools

## Slide 5: Project Programming
High School Credit Recovery
  2 semesters; year long
    Physics– Spring 2024
    Algebra 1 – Summer 2024
    Geometry – Summer 2024
    Algebra 2 – Summer 2024
Using Critical Place-Based Pedagogy to infuse cultural relevance for learners.

## Slide 6: Project Programming
Community Modules
    Infant Safety (car seats, choking, falls, etc)
    Understanding IEPs (parents and caregivers)
Dual Credit – Luna Community College
    Introduction to Teaching (EDUC 1120)
    Introduction to Special Education (SPED 2110)
    English Comp I
Collaboration of NMHU Community and Education partners

## Slide 7: Overall Project Progress
Revised Timeline (September 2023)
Fall 2022 – Funding received; Director hired
Spring 2023 – Personnel hired; Begin Program development & Anchor Community planning
Summer 2023 – Hardware procured; Continued program and community planning
Fall 2023 – Program build; 1st hardware distribution; community outreach; OER planning
  November pilot of community modules to test systems and outreach strategy
Spring 2024 – Regional pilot - credit recovery, dual credit and community courses; 2nd hardware distribution;
Summer 2024 – Sustainment planning; Add modules per need
Fall 2024 – Full program launch; Sustainment & Summative Report
Original Timeline (November 2022)
Fall 2022 – Project Launch
Spring 2023 – Personnel Hiring, Program Development & Anchor Community Planning
Summer 2023 – Anchor Community Pilot (1-2 modules)
Fall 2023 – Anchor Community Rollout
Spring 2024 – Regional pilot – Identify additional needs
Summer 2024 – Sustainment Planning & Add modules per need
Fall 2024 – Sustainment & Summative Report
Despite three month initial delay, timeline still on track for rollout/launch and sustainment.

## Slide 8: Overall Project Progress
Accomplishments
    High School credit recovery added
    Additional School Districts joining efforts – 5 year MOUs
    Leveraging NM statewide K-12 network for LMS and OER outreach (NM PED)
    San Miguel County Early Childhood Coalition (streamlined networking)
    Connections with NM Forest and Watershed Restoration Institute – programming, outreach, experiential learning
    Using Critical Place-Based Pedagogy to infuse cultural relevance for learners. ALGE experts in NNM as SMEs.
    All programming will be OERs (open education resources) available nationally.
Tech tackling “education deserts”
Connecting to more rural districts
TCC Program aligns with NM state ed needs (Yazzie/Martinez; bi-lingual; teacher shortage)
Open Education Resources – accessible archives
Teacher and Content Sustainment

## Slide 9: Overall Project Progress
Barriers
    Anchor School Districts’ welcome involvement, have additional challenges
    Program/course build timelines on semester schedules
    Full time faculty overloaded and overstretched
Opportunities
    Developed a menu of courses to meet HS partners’ needs
    Reassess program needs
      Switch to dual credit education track (Educators Rising) & credit recovery
    Hiring full-time Content Developers (vs. contractors)
    Partnering with forward-thinking educators and cultural experts
Barriers became opportunities.
Building trust and understanding.

## Slide 10: Equipment & Networking Activities
Approved for 350 laptops and support hardware (charging carts, storage)
  200 laptops on site (July); 100 laptops being shipped (12 Sep)
  84 laptops distributed August 14 – beginning of NMHU Fall Semester
    100 were available. (Press Release)
  Additional distributions in January 2024 (existing college students) and August 2024 (high school graduates entering college)
Getting the technology to those that need it most
Students were thrilled by the opportunity provided!

## Slide 11
APPENDIX

## Slide 12
Technology
Education
Knowledge
Community
Foundation, essential, culture & language
Shared learning experience
Students, teachers, mode, type, partnerships, training
Last mile connectivity options for career learning & success
Technology Connected Communities (TCC)
Core Concepts

## Slide 13
Technology
Education
Knowledge
Community
Life force
Heart
Past & future
identity
Land
Water
Culture
shared
learning
experience
Colleges
Districts
Associations
Teachers
Elders
Students
Libraries
PED
HED
Last Mile Connectivity
TCC Project
NTIA Grant
Hardware/Software
Technology Connected Communities (TCC)

## Slide 14: Project Action (with Aims)
Collaborate with ALGE Project and NNM Communities
  Sustain community identity and integrity.
Build culturally and linguistically responsive content modules
  Elevate culture and language learning.
Work with local anchor communities in NNM to provide dual credit and credit recovery options
  Support education connections.
Use grant resources to provide “last mile” connectivity, hardware/software, online badging
  Leverage technology options.
Advance job, college and career options through high schools, trades and colleges
  Promote Northern New Mexico community legacy through career success.

## Slide 16: Power of Partner Collaboration
Mini Summits
January 20, 2024
April 20, 2024
Summer Summit
June 3-7, 2024
Priority
The need to align contributions and initiatives.